## Assembly Schedule
Assembly Schedule
Cell | SO # / Rel | Customer | Part Number | Ship Date | Dock Date | Projected Completion | JO/PO Open | JO/PO Quantity | Assembly Tool Status | Tool Proj Compl Date | Assembly Rout Valid | Cycle Time Valid | JO/PO Notes | FAI | FAI Type | SO Bklg Qty | On Hand Stock | On Hand CR / QA | JO/PO In Proc | Assy Time | Kit Status | Status
BLUE |  | Southern Mechanics Corp. | 10000000ADS-001 | 2016-01-30 | 2016-03-31 | 2016-04-01 |  | 0 | Yes |  | Yes | ENTER |  | NO |  | 1500 | 2005 | 0
BLUE |  | Narantics Company | 10000000ADS-002 | 2016-01-30 | 2016-03-31 | 2016-04-02 |  | 98 | Yes |  | Yes | ENTER |  | NO |  | 750 | 0 | 0 | 2000 | 10.57 | Build
BLUE |  | HaroCorp | 10000000ADS-003 | 2016-01-30 | 2016-03-31 | 2016-04-05 |  | 4 | Yes |  | Yes | ENTER |  | NO |  | 300 | 253 | 0
BLUE |  | HaroCorp | 10000000ADS-004 | 2016-01-30 | 2016-03-31 | 2016-04-05 |  | 5 | Yes |  | Yes | ENTER |  | NO |  | 92 | 125 | 0
BLUE |  | Cavarka Enterprises | 10000000ADS-005 | 2016-01-30 | 2016-04-16 | 2016-04-18 |  | 12 | Yes |  | Yes | ENTER |  | NO |  | 58 | 97 | 0
BLUE |  | Roffman-Solo | 10000000ADS-006 | 2016-01-30 | 2016-04-16 | 2016-04-18 |  | 233 | Yes |  | Yes | ENTER |  | NO |  | 600 | 0 | 0 | 5000 | 2.4286 | Build
BLUE |  | Boca-Reighns | 10000000ADS-007 | 2015-02-05 | 2016-06-08 | 2016-06-10 |  | 43 | Yes |  | Yes | ENTER |  | NO |  | 32 | 0 | 0 | 50 | 0.45 | Build
BLUE |  | Boca-Reighns | 10000000ADS-008 | 2015-02-05 | 2016-06-08 | 2016-06-12 |  | 3 | Yes |  | Yes | ENTER |  | NO |  | 73 | 0 | 0 | 100 | 0.93667 | Build
BLUE |  | KPI Holdings | 10000000ADS-009 | 2016-02-06 | 2016-06-08 | 2016-06-12 |  | 55 | Yes |  | Yes | ENTER |  | NO |  | 320 | 8 | 0 | 3100 | 4.8325 | Build
BLUE |  | KPI Holdings | 10000000ADS-010 | 2016-02-06 | 2016-06-08 | 2016-06-12 |  | 356 | Yes |  | Yes | ENTER |  | NO |  | 900 | 0 | 0 | 1000 | 8.6611 | Inc Kit
BLUE |  | Sukaromko Group | 10000000ADS-011 | 2016-02-08 | 2016-06-10 | 2016-06-14 |  | 24 | Yes |  | Yes | ENTER |  | NO |  | 50 | 8 | 0 | 3100 | 1.933 | Build
|  | Total Items: 38 | [17 empty] | 103.2255 | 18