## Forecast Report
Forecast Report
Part Number | Description | JO/ SO | SO | Prod Cls | Job | Job Status | Program | Date | Due Date | Contract/ Sched Fin Date | Job or Order Qty | On Hand/ Avail | BO or Production Qty | BO Amount | Expected Production | Ready To Move | Cost To Date | ETC Material | ETC Labor | ETC Overheadl | ETC | EAC Material | EAC Labor | EAC Overheadl | EAC | EAC Qty | EAC Per Piece | Projected Margin Per Piece | Projected Revenue | Projected Margin | Percent Margin
Value Stream Ant
011-0113-0001 | [11 empty] | 20 | [12 empty] | Std Cost: |  | 277.9109
011-0113-0001 | ANTENNA,10 INCH ARRAY | SO |  | AW |  |  | WEATHER RADAR | 2014-03-21 | 2014-03-21 | 2014-03-21 | 1 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
011-0113-0001 | ANTENNA,10 INCH ARRAY | JO |  | AN |  | RELEASED | WEATHER RADAR | 2015-09-22 | 2015-09-22 | 2015-09-22 | 10 | 29 | 10 | 0 | 10 | 0 | 2962.4144 | 7.2 | 0 | 0 | 7.2 | 1145.5511 | 413.6178 | 1410.4455 | 2969.6144 | 10 | 296.9614 |  | 0
011-0113-0001 | ANTENNA,10 INCH ARRAY | SO |  | AN |  |  | WEATHER RADAR | 2016-01-25 | 2016-01-25 | 2016-01-31 | 2 | 27 | 2 | 680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
011-0113-0001 | ANTENNA,10 INCH ARRAY | SO |  | AN |  |  | WEATHER RADAR | 2016-01-25 | 2016-01-25 | 2016-01-31 | 11 | 16 | 11 | 3740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
011-0113-0001 | ANTENNA,10 INCH ARRAY | SO |  | AN |  |  | WEATHER RADAR | 2016-01-27 | 2016-01-27 | 2016-02-03 | 5 | 11 | 5 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
011-0113-0001 | [9 empty] | Tl SO Qty: | 19 | 11 | 19 | 6120 | 10 | 0 | 2962.4144 | 7.2 | 0 | 0 | 7.2 | 1145.5511 | 413.6178 | 1410.4455 | 2969.6144 | 10 | 296.9614 | 25.1438 | 6120 | 477.7326 | 7.806%
[8 empty] | On Hand: | 20 | Tl Job Qty: | 10 |  | 10 | 322.1053 | Proj Ship: | 19
900-0001-1111 | [11 empty] | 8 | [12 empty] | Std Cost: |  | 423.857
900-0001-1111 | ANTENNA,12 INCH ARRAY | SO |  | AN |  |  | WEATHER RADAR | 2016-01-11 | 2016-01-11 | 2016-01-18 | 3 | 5 | 3 | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
900-0001-1111 | ANTENNA,12 INCH ARRAY | SO |  | AN |  |  | WEATHER RADAR | 2016-01-13 | 2016-01-13 | 2016-01-20 | 1 | 4 | 1 | 678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
900-0001-1111 | ANTENNA,12 INCH ARRAY | SO |  | AN |  |  | WEATHER RADAR | 2016-01-31 | 2016-01-31 | 2016-01-18 | 3 | 1 | 3 | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
900-0001-1111 | ANTENNA,12 INCH ARRAY | SO |  | AN |  |  | WEATHER RADAR | 2016-01-31 | 2016-01-31 | 2016-03-07 | 1 | 0 | 1 | 678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
900-0001-1111 | ANTENNA,12 INCH ARRAY | SO |  | AN |  |  | WEATHER RADAR | 2016-01-31 | 2016-01-31 | 2016-05-01 | 1 | -1 | 1 | 678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
900-0001-1111 | ANTENNA,12 INCH ARRAY | SO |  | AN |  |  | WEATHER RADAR | 2016-01-31 | 2016-01-31 | 2016-08-29 | 1 | -2 | 1 | 678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
900-0001-1111 | [9 empty] | Tl SO Qty: | 10 | -2 | 10 | 6780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254.143 | 5424 | 2033.1437 | 37.48%
[8 empty] | On Hand: | 8 | Tl Job Qty: | 0 |  | 0 | 678 | Proj Ship: | 8
322-2321-0011 | [11 empty] | 0 | [12 empty] | Std Cost: |  | 570.9128
322-2321-0011 | ANTENNA ARRAY, GWX 70/75,10 IN | JO |  | AN |  | RELEASED | WEATHER RADAR | 2015-11-06 | 2015-11-06 | 2015-11-06 | 10 | 2 | 2 | 0 | 2 | 0 | 3504.42 | 180.7396 | 45.3925 | 137.4114 | 363.5435 | 966.9196 | 756.4725 | 2144.5714 | 3867.9635 | 10 | 386.7964 |  | 0
322-2321-0011 | ANTENNA ARRAY, GWX 70/75,10 IN | JO |  | AN |  | RELEASED | WEATHER RADAR | 2015-11-18 | 2015-11-18 | 2015-11-18 | 10 | 12 | 10 | 0 | 10 | 0 | 4090.52 | 215.1396 | 96.6263 | 298.2424 | 610.0083 | 785.9596 | 962.5263 | 2952.0424 | 4700.5283 | 10 | 470.0528 |  | 0
322-2321-0011 | ANTENNA ARRAY, GWX 70/75,10 IN | JO |  | AN |  | RELEASED | WEATHER RADAR | 2015-11-20 | 2015-11-20 | 2015-11-20 | 10 | 18 | 6 | 0 | 6 | 0 | 9022.35 | 202.2396 | 48.2545 | 148.451 | 398.9451 | 785.9596 | 2856.2545 | 5779.081 | 9421.2951 | 10 | 942.1295 |  | 0
322-2321-0011 | ANTENNA ARRAY, GWX 70/75,10 IN | JO |  | AN |  | RELEASED | WEATHER RADAR | 2015-11-23 | 2015-11-23 | 2015-11-23 | 10 | 19 | 1 | 0 | 1 | 0 | 4015 | 176.4396 | 0 | 0 | 176.4396 | 785.9596 | 943.93 | 2461.55 | 4191.4396 | 10 | 419.144 |  | 0
322-2321-0011 | ANTENNA ARRAY, GWX 70/75,10 IN | SO |  | AN |  |  | WEATHER RADAR | 2016-01-15 | 2016-01-15 | 2015-12-23 | 25 | 13 | 6 | 5898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
322-2321-0011 | ANTENNA ARRAY, GWX 70/75,10 IN | SO |  | AN |  |  | WEATHER RADAR | 2016-01-15 | 2016-01-15 | 2015-12-23 | 50 | -37 | 50 | 49150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
322-2321-0011 | [9 empty] | Tl SO Qty: | 75 | -37 | 56 | 55048 | 19 | 0 | 20632.29 | 774.5584 | 190.2733 | 584.1048 | 1548.9365 | 3324.7984 | 5519.1833 | 13337.2448 | 22181.2265 | 40 | 554.5307 | 428.4693 | 18677 | 8140.9174 | 43.59%
[8 empty] | On Hand: | 0 | Tl Job Qty: | 40 |  | 19 | 983 | Proj Ship: | 19