## Job Actuals Non-Shippable Only
Job Actuals - Non-Shippable Only (based on a snapshot)
Job Number | Status | Part # | Rev | DL Prod | DL Setup | Total DL | DL Variance | L w/OH ETC | DM | DM Other | DM Subc | DM Tooling | Total DM | DM Variance | M w/OH ETC | Overhead | Estimate | Actual | Variance | SO # | Status | Actual Release | Close Date | Program / Project | Quantity | Part Description
SJS10-0001 | COMPLETED | 1000000-00G1 | X- | 133.16 | 0 | 133.16 | 0 | 3.0562 | 43.3949 | 0 | 0 | 0 | 43.3949 | 0.8449 | 0 | 529.45 | 214.208 | 176.5549 | 0 |  | COMPLETED | 2016-01-08 |  |  | 5
SJS10-0002 | RELEASED | 1000000-00G2 | X- | 0.52 | 0 | 0.52 | 0 | 1259.6474 | 78.281 | 0 | 0 | 0 | 78.281 | 1.691 | 0 | 2.69 | 357.1104 | 78.801 | 0 |  | RELEASED | 2016-01-08 |  |  | 5
SJS10-0003 | RELEASED | 1000000-00G3 | C | 5.68 | 0 | 5.68 | 0 | 1443.5016 | 1483.9709 | 0 | 0 | 0 | 1483.9709 | 0 | 214.6625 | 29.59 | 2124.3167 | 1489.6509 | 0 |  | RELEASED | 2016-01-08 |  |  | 7
SJS10-0004 | RELEASED | 1000000-00G4 | - | 1.03 | 0 | 1.03 | 0 | 652.5768 | 1039.075 | 0 | 0 | 0 | 1039.075 | 1039.075 | 0 | 5.38 | 134.0925 | 1040.105 | 906.0125 |  | RELEASED | 2016-01-11 |  |  | 16
SJS10-0005 | RELEASED | 1000000-00G5 | NS | 0 | 0 | 0 | 0 | 605.088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93.984 | 0 | 0 |  | RELEASED | 2016-01-19 |  |  | 33
SJS10-0006 | RELEASED | 1000000-00G6 | - | 88.33 | 0 | 88.33 | 0 | 563.832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 344.85 | 168.1059 | 88.33 | 0 |  | RELEASED | 2016-01-07 |  |  | 2
SJS10-0007 | RELEASED | 1000000-00G7 | NS | 366.3 | 0 | 366.3 | 366.3 | 0.09168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 366.3 | 366.3 |  | RELEASED | 2016-01-11 |  |  | 1
SJS10-0008 | COMPLETED | 1000000-00G8 | - | 215.09 | 0 | 215.09 | 161.0276 | 0 | 458.2097 | 0 | 0 | 0 | 458.2097 | 0 | 0 | 678.01 | 512.326 | 673.2997 | 160.9737 |  | COMPLETED | 2016-01-07 |  |  | 1
SJS10-0009 | RELEASED | 1000000-00G9 | - | 0 | 0 | 0 | 0 | 111.8498 | 719.1 | 0 | 0 | 0 | 719.1 | 0 | 80.804 | 0 | 761.8447 | 719.1 | 0 |  | RELEASED | 2016-01-07 |  |  | 1
SJS10-0010 | CLOSED | 1000000-00G10 | X- | 83.91 | 0 | 83.91 | 40.2666 | 0 | 4.8 | 0 | 0 | 0 | 4.8 | 0 | 0 | 271.48 | 48.4434 | 88.71 | 40.2666 |  | CLOSED | 2016-01-07 |  |  | 12
SJS10-0011 | CLOSED | 1000000-00G11 | NS | 66.17 | 0 | 66.17 | 45.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192.6 | 20.76 | 66.17 | 45.41 |  | CLOSED | 2016-01-04 |  |  | 1
SJS10-0012 | RELEASED | 1000000-00G12 | NS | 754.44 | 0 | 754.44 | 0 | 3667.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2416.51 | 1107.2 | 754.44 | 0 |  | RELEASED | 2016-01-06 |  |  | 1
SJS10-0013 | COMPLETED | 1000000-00G13 | NS | 36.15 | 0 | 36.15 | 15.3493 | 24.7536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117.11 | 20.8007 | 36.15 | 15.3493 |  | COMPLETED | 2016-01-07 |  |  | 1
SJS10-0014 | COMPLETED | 1000000-00G14 | NS | 49.66 | 0 | 49.66 | 28.8593 | 24.7536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.64 | 20.8007 | 49.66 | 28.8593 |  | COMPLETED | 2016-01-07 |  |  | 1
SJS10-0015 | RELEASED | 1000000-00G15 | NS | 40.38 | 0 | 40.38 | 0 | 71.5104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150.44 | 44.2482 | 40.38 | 0 |  | RELEASED | 2016-01-14 |  |  | 1
SJS10-0016 | RELEASED | 1000000-00G16 | NS | 167.32 | 0 | 167.32 | 42.2828 | 239.2849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 474.99 | 125.0372 | 167.32 | 42.2828 |  | RELEASED | 2016-01-14 |  |  | 1
SJS10-0017 | RELEASED | 1000000-00G17 | B | 98.97 | 0 | 98.97 | 0 | 3025.4411 | 21986.7615 | 0 | 0 | 0 | 21986.7615 | 2814.1435 | 0 | 231.96 | 20264.189 | 22085.7315 | 1821.5425 |  | RELEASED | 2016-01-20 |  |  | 4
SJS10-0018 | COMPLETED | 1000000-00G18 | B | 787.7109 | 0 | 787.7109 | 441.486 | 0 | 465 | 0 | 0 | 0 | 465 | 0 | 0 | 2071.1678 | 811.2249 | 1252.7109 | 441.486 |  | COMPLETED | 2016-01-08 |  |  | 1
SJS10-0019 | RELEASED | 1000000-00G19 | B | 1162.4944 | 0 | 1162.4944 | 961.8479 | 27.5041 | 180.8192 | 0 | 0 | 0 | 180.8192 | 61.1842 | 0 | 3163.5082 | 320.2815 | 1343.3136 | 1023.0321 |  | RELEASED | 2016-01-11 |  |  | 1
SJS10-0020 | COMPLETED | 1000000-00G20 | A | 96.09 | 0 | 96.09 | 85.287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 293.91 | 10.803 | 96.09 | 85.287 |  | COMPLETED | 2016-01-05 |  |  | 4
SJS10-0021 | COMPLETED | 1000000-00G21 | B | 390.73 | 0 | 390.73 | 274.8491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1101.94 | 115.8809 | 390.73 | 274.8491 |  | COMPLETED | 2016-01-11 |  |  | 1