## Machine Shop Schedule
Machine Shop Schedule
Excluding Finished Jobs
Work Center | Mach # | Job # | Delta Part Number | Rev | Qty | Rel Date | Due Date | Projected Completion | Seq | Production Status | Setup Machinist | Shift | RM Part # | Raw Material | Setup Hours | PPH per M2M | Total Hours | Program | Standard Tool List | Job Tool List | JO Notes
AERO 23 PL | 2Q | AB10C-0000 | 01-23456-01-AB | - | 100 | 2015-10-01 | 2016-01-11 |  | 1 | Setup |  | 1 | 10001 |  | 4 | 50 | 6 |  | YES | NO | ENTER
AERO 23 PL | 2Q | AB10C-0001 | 01-23456-02-AB | A | 2000 | 2015-12-01 | 2016-01-11 |  | 5 | ----- |  |  | 10001 |  | 4 | 1111 | 5.8002 |  | NO | NO | ENTER
AERO 23 PL | 2Q | AB10C-0002 | 01-23456-03-AB | A | 500 | 2015-12-17 | 2016-01-14 |  | 20 | ----- |  |  | 10001 |  | 4 | 130 | 7.8462 |  | YES | NO | ENTER
AERO 23 PL | 2Q | AB10C-0003 | 01-23456-04-AB | D | 50 | 2015-12-21 | 2016-01-14 |  | 25 | ----- |  |  | 10001 |  | 4 | 80 | 4.625 |  | NO | NO | 12/21 Quote ov (SM)
AERO 23 PL | 2Q | AB10C-0004 | 01-23456-05-AB | A | 25 | 2015-12-17 | 2016-01-14 |  | 30 | ----- |  |  | 10001 |  | 4 | 60 | 4.4167 |  | NO | NO | 12/21 quote ov (SM)
AERO 23 PL | 2Q | AB10C-0005 | 01-23456-06-AB | E | 7000 | 2015-10-12 | 2016-01-15 |  | 35 | ----- |  |  | 10001 |  | 4 | 65 | 111.6923 |  | YES | KITTED | ENTER
AERO 23 PL | 2Q | AB10C-0006 | 01-23456-07-AB | - | 200 | 2015-12-08 | 2016-01-16 |  | 40 | ----- |  |  | 10001 |  | 6 | 55 | 9.6364 |  | NO | NO | 12/9 Quote ov (SM)
AERO 23 PL | 2Q | AB10C-0007 | 01-23456-08-AB | A | 600 | 2015-11-04 | 2016-01-19 |  | 50 | ----- |  |  | 10001 |  | 4 | 70 | 12.5714 |  | YES | YES | ENTER
AERO 23 PL | 2Q | AB10C-0008 | 01-23456-09-AB | A | 400 | 2015-12-22 | 2016-01-19 |  | 55 | ----- |  |  | 10001 |  | 4 | 75 | 9.3333 |  | YES | NO | ENTER
AERO 23 PL | 2Q | AB10C-0009 | 01-23456-11-AB | B | 400 | 2015-11-04 | 2016-01-19 |  | 60 | ----- |  |  | 10001 |  | 4 | 90 | 8.4444 |  | NO | NO | ENTER
AERO 23 PL | 2Q | AB10C-0010 | 01-23456-12-AB | A | 300 | 2015-11-13 | 2016-04-03 |  | 70 | ----- |  |  | 10001 |  | 4 | 92 | 7.2609 |  | YES | NO | ENTER
AERO 23 PL | 2Q | AB10C-0011 | 01-23456-13-AB | G | 1000 | 2015-11-11 | 2016-01-31 |  | 80 | ----- |  |  | 10001 |  | 4 | 95 | 14.5263 |  | YES | NO | 12/21 PULLED IN FROM 3/20 (SM)
AERO 23 PL | 2Q | AB10C-0012 | 01-23456-14-AB | - | 5000 | 2015-11-18 | 2016-02-15 |  | 90 | ----- |  |  | 10001 |  | 4 | 52 | 100.1538 |  | YES | NO | ENTER
AERO 23 PL | 2Q | AB10C-0013 | 01-23456-15-AB | D | 10000 | 2015-12-28 | 2016-03-15 |  | 95 | ----- |  |  | 10001 |  | 4 | 66 | 155.5152 |  | YES | NO | ENTER
AERO 23 PL | 2Q | AB10C-0014 | 01-23456-16-AB | B | 1000 | 2015-11-12 | 2016-05-02 |  | 100 | ----- |  |  | 10001 |  | 4 | 113 | 12.8496 |  | YES | NO | ENTER
AERO 23 PL | 2Q | AB10C-0015 | Jobs: 15 | [11 empty] | 62 |  | 470.6716
AERO 23 PL | 9S | AB10C-0016 | 01-23456-16-AB | B | 100 | 2015-12-21 | 2016-01-04 |  | 1 | Setup |  | 1 | 20001 |  | 4 | 52 | 5.9231 |  | YES | NO | ENTER
AERO 23 PL | 9S | AB10C-0017 | 01-23456-17-AB | E | 2500 | 2015-12-03 | 2016-01-05 |  | 5 | ----- |  |  | 20001 |  | 6 | 40 | 68.5 |  | YES | NO | ENTER
AERO 23 PL | 9S | AB10C-0018 | 01-23456-18-AB | B | 3500 | 2015-12-08 | 2016-01-05 |  | 10 | ----- |  |  | 20001 |  | 5 | 120 | 34.1667 |  | NO | NO | ENTER
AERO 23 PL | 9S | AB10C-0019 | 01-23456-19-AB | - | 500 | 2015-12-17 | 2016-01-18 |  | 25 | ----- |  |  | 20001 |  | 4 | 65 | 11.6923 |  | NO | NO | ENTER
AERO 23 PL | 9S | AB10C-0020 | 01-23456-20-AB | A | 1000 | 2015-12-10 | 2016-01-25 |  | 30 | ----- |  |  | 20001 |  | 6 | 26 | 44.4615 |  | YES | NO | ENTER
AERO 23 PL | 9S | AB10C-0021 | 01-23456-21-AB | E | 5000 | 2015-12-07 | 2016-02-15 |  | 50 | ----- |  |  | 20001 |  | 4 | 44 | 117.6364 |  | YES | NO | ENTER
AERO 23 PL | 9S | AB10C-0022 | 01-23456-22-AB | - | 4800 | 2015-12-16 | 2016-02-22 |  | 60 | ----- |  |  | 20001 |  | 4 | 45 | 110.6667 |  | YES | NO | ENTER
AERO 23 PL | 9S | AB10C-0023 | 01-23456-23-AB | A | 350 | 2015-12-07 | 2016-02-25 |  | 70 | ----- |  |  | 20001 |  | 4 | 40 | 12.75 |  | YES | NO | ENTER
AERO 23 PL | 9S | AB10C-0024 | 01-23456-24-AB | - | 150 | 2015-12-10 | 2016-02-29 |  | 75 | ----- |  |  | 20001 |  | 2.5 | 66 | 4.7727 |  | NO | NO | ENTER
AERO 23 PL | 9S | AB10C-0025 | 01-23456-25-AB | E | 2500 | 2015-12-10 | 2016-04-15 |  | 90 | ----- |  |  | 20001 |  | 6 | 40 | 68.5 |  | YES | NO | 12/15 DATE SHOULD BE 2016 (SM)
AERO 23 PL | 9S |  | Jobs: 10 | [11 empty] | 45.5 |  | 479.0693