## Work Center Actual Performance
Work Center Actual Performance
Value Stream | Job | Oper | Operation Description | Work Center | Status | Part | Oper Qty | Actual Qty Comp | This Period Qty Comp | Pct Comp | Est Hrs | Actual Labor Hrs | Variance Hrs | This Period Labor Hrs | Last Labor | Scheduled Finish | Estimated Setup | Estimated Run/Pc | Actual Setup | Actual Run/Pc | Change Setup Time To | Change Run Time To | Comments
Value Stream: Ant
Ant | SJSA-10001 | 1 |  | 1001 | RELEASED | 30239-ADS-01 | 6 | 5 | 5 | 100 | 16.55 | 8.41 | -8.14 | 1.05 | 2016-01-25 08:37 | 2016-02-02 | 0.05 | 2.75 | 0 | 1.672
Ant | SJSA-10002 | 2 |  | 1001 | RELEASED | 30239-ADS-02 | 4 | 4 | 0 | 100 | 2.8268 | 6.83 | 4.0032 | 0.2 | 2016-01-25 06:49 | 2016-01-25 | 0.5 | 0.5817 | 0 | 1.5825
Ant | SJSA-10003 | 3 |  | 1001 | RELEASED | 30239-ADS-03 | 4 | 4 | 0 | 100 | 4.12 | 7.47 | 3.35 | 0.76667 | 2016-01-25 10:14 | 2016-01-27 | 0.44 | 0.92 | 0 | 1.7575
Ant | SJSA-10004 | 4 |  | 1001 | RELEASED | 30239-ADS-04 | 1 | 1 | 1 | 100 | 1.15 | 3.93 | 2.78 | 3.9333 | 2016-01-25 10:08 | 2016-01-04 | 0.17 | 0.98 | 0 | 3.76
Ant | SJSA-10005 | 5 |  | 1001 | RELEASED | 30239-ADS-05 | 6 | 6 | 6 | 100 | 24.25 | 21.81 | -2.44 | 1.45 | 2016-01-25 07:54 | 2016-02-11 | 0.25 | 4 | 0 | 3.5933
Ant | SJSA-10006 | 6 |  | 1001 | RELEASED | 30239-ADS-06 | 5 | 5 | 0 | 100 | 0.17 | 2.55 | 2.38 | 2.0167 | 2016-01-25 08:34 | 2015-12-11 | 0.17 | 1e-06 | 0 | 0.476
Ant | SJSA-10007 | 7 |  | 1001 | RELEASED | 30239-ADS-07 | 5 | 5 | 5 | 100 | 8.1167 | 9.6 | 1.4833 | 0.83333 | 2016-01-25 07:18 | 2015-12-16 | 0.25 | 1.5733 | 0 | 1.87
Ant | SJSA-10008 | 8 |  | 1001 | RELEASED | 30239-ADS-08 | 3 | 3 | 0 | 100 | 0.56 | 1.9 | 1.34 | 1.1667 | 2016-01-25 07:44 | 2016-01-06 | 0.05 | 0.17 | 0 | 0.61667
Ant | SJSA-10009 | 9 |  | 1001 | RELEASED | 30239-ADS-09 | 10 | 10 | 10 | 100 | 3.91 | 5.13 | 1.22 | 1.6833 | 2016-01-25 07:43 | 2016-01-08 | 0.05 | 0.386 | 0 | 0.508
Ant | SJSA-10010 | 10 |  | 1001 | RELEASED | 30239-ADS-10 | 1 | 1 | 1 | 100 | 0.585 | 1.63 | 1.045 | 1.6333 | 2016-01-25 08:41 | 2016-01-04 | 0.08 | 0.505 | 0 | 1.55
Ant | SJSA-10011 | 11 |  | 1001 | RELEASED | 30239-ADS-11 | 4 | 4 | 0 | 100 | 0.87 | 1.39 | 0.52 | 0.98333 | 2016-01-25 07:26 | 2016-01-28 | 0.27 | 0.15 | 0 | 0.28
Ant | SJSA-10012 | 12 |  | 1001 | COMPLETED | 30239-ADS-12 | 6 | 6 | 6 | 100 | 0.47 | 0.22 | -0.25 | 0.21667 | 2016-01-25 10:29 | 1899-12-31 | 0.17 | 0.05 | 0 | 0.0083333
Ant | SJSA-10013 | 13 |  | 1001 | RELEASED | 30239-ADS-13 | 5 | 5 | 5 | 100 | 0.35 | 0.1 | -0.25 | 0.1 | 2016-01-25 09:14 | 2015-12-17 | 0.05 | 0.06 | 0 | 0.01
Ant | SJSA-10014 | 14 |  | 1001 | RELEASED | 30239-ADS-14 | 1 | 1 | 1 | 100 | 0.25 | 0.02 | -0.23 | 0.01667 | 2016-01-25 07:25 | 2016-02-08 | 0.25 | 1e-06 | 0 | -0.23
Ant | SJSA-10015 | 15 |  | 1001 | RELEASED | 30239-ADS-15 | 1 | 1 | 1 | 100 | 0.81 | 0.58 | -0.23 | 0.58333 | 2016-01-25 09:16 | 2016-01-14 | 0.17 | 0.64 | 0 | 0.41